## Blad1
Project 2018 / 2019 Embedded and Mobile System
Minedestroyers (Group 5)
| TASK | RESPONSIBLE | HOURS EACH TASK | HOURS TOTAL
1 | Development |  |  |  | Tasks | Start date | Workdays to complete
1.1 | Preperations |  | 46 | 54 | Circuit schematic | 2019-01-14 | 2
1.1.1 | Circuit schematic | Al-Husein | 8 | 8 | Setup Github | 2019-01-14 | 0.5
1.1.2 | Setup Github | All | 2 | 10 | Assembly car | 2019-01-16 | 1
1.1.3 | Assembly car | Al-Husein | 4 | 4 | Calculate powerdraw | 2019-01-14 | 2
1.1.4 | Calculate powerdraw | Andreas | 8 | 8 | Supply robot with power | 2019-01-16 | 1
1.1.5 | Supply robot with power | Andreas | 4 | 4 | Build chassis extension arm | 2019-01-14 | 5
1.1.6 | Build chassis extension arm | Antonio | 20 | 20 | Research | 2019-01-17 | 2
1.2 | Motors |  | 45 | 45 | Config CubeMX | 2019-01-22 | 0.25
1.2.1 | Research | Andreas | 8 | 8 | Move motor with set speed | 2019-01-22 | 3.75
1.2.2 | Config CubeMX | Andreas | 1 | 1 | Control motor with events | 2019-01-29 | 2.75
1.2.3 | Move motor with set speed | Andreas | 15 | 15 | Control motor with states | 2019-01-31 | 2.5
1.2.4 | Control motor with events | Andreas | 11 | 11 | Research | 2019-01-14 | 1.25
1.2.5 | Control motor with states | Andreas | 10 | 10 | Config CubeMX | 2019-01-16 | 0.25
1.3 | Obstacle |  | 51 | 51 | Implement trigger | 2019-01-16 | 1.5
1.3.1 | Ultrasound |  | 22 | 22 | Send event at set distance | 2019-01-18 | 1
1.3.1.1 | Research | Fleury | 5 | 5 | Statemachine to recieve event | 2019-01-21 | 1
1.3.1.2 | Config CubeMX | Fleury | 1 | 1 | Test | 2019-01-22 | 0.5
1.3.1.3 | Implement trigger | Fleury | 6 | 6 | Turn at obstacle | 2019-01-14 | 3.75
1.3.1.4 | Send event at set distance | Fleury | 4 | 4 | Test | 2019-01-18 | 0.75
1.3.1.5 | Statemachine to recieve event | Fleury | 4 | 4 | Queue for sensor events | 2019-01-20 | 2
1.3.1.6 | Test | Fleury | 2 | 2 | Test | 2019-01-22 | 0.75
1.3.2 | Turn at obstacle | William | 15 | 15 | Research | 2019-01-17 | 0.75
1.3.2.1 | Test | William | 3 | 3 | Config CubeMX | 2019-01-18 | 0.25
1.3.3 | Queue for sensor events | William | 8 | 8 | Statemachine to recieve event | 2019-01-18 | 0.75
1.3.3.1 | Test | William | 3 | 3 | PWM control pitch | 2019-01-19 | 0.75
1.4 | Mines |  | 74 | 74 | Test | 2019-01-19 | 0.5
1.4.1 | Buzzer |  | 12 | 12 | Research | 2019-01-23 | 3
1.4.1.1 | Research | Al-Husein | 3 | 3 | Config CubeMX | 2019-01-28 | 0.25
1.4.1.2 | Config CubeMX | Al-Husein | 1 | 1 | Statemachine to recieve event | 2019-01-28 | 2.25
1.4.1.3 | Statemachine to recieve event | Al-Husein | 3 | 3 | Send event depending on color | 2019-01-30 | 2.5
1.4.1.4 | PWM control pitch | Al-Husein | 3 | 3 | Test | 2019-02-01 | 1.25
1.4.1.5 | Test | Al-Husein | 2 | 2 | Research | 2019-01-21 | 2.75
1.4.2 | Color sensor |  | 37 | 37 | Config CubeMX | 2019-01-23 | 0.25
1.4.2.1 | Research | William | 12 | 12 | Statemachine to recieve event | 2019-01-23 | 2
1.4.2.2 | Config CubeMX | William | 1 | 1 | Test | 2019-01-25 | 1.25
1.4.2.3 | Statemachine to recieve event | William | 9 | 9 | Vibrate | 2019-01-28 | 2.75
1.4.2.4 | Send event depending on color | William | 10 | 10 | Show color off mine | 2019-01-23 | 2.75
1.4.2.5 | Test | William | 5 | 5 | List coordinates for obsticles and mines | 2019-01-31 | 5.75
1.4.3 | RGB-LED |  | 25 | 25 | Show area covered | 2019-02-03 | 4.75
1.4.3.1 | Research | Antonio | 11 | 11 | Start / Stop robot | 2019-02-04 | 2.5
1.4.3.2 | Config CubeMX | Antonio | 1 | 1 | Instruction manual | 2019-02-06 | 1.75
1.4.3.3 | Statemachine to recieve event | Antonio | 8 | 8 | Test | 2019-02-08 | 0.5
1.4.3.4 | Test | Antonio | 5 | 5 | Mockup | 2019-02-01 | 1.75
1.5 | App |  | 113 | 195 | Implement mockup | 2019-02-04 | 2.75
1.5.1 | Research | All | 4 | 20 | Test | 2019-02-07 | 2
1.5.2 | Functionality |  | 83 | 121 | Get connection with app | 2019-02-06 | 4
1.5.2.1 | Vibrate | Antonio | 11 | 11 | Process data from app | 2019-02-08 | 5.25
1.5.2.2 | Show color off mine | Fleury | 11 | 11 | Send data | 2019-02-11 | 4
1.5.2.3 | List coordinates for obsticles and mines | Antonio,Al-Husein | 23 | 46 | Bluetooth activity LED | 2019-02-20 | 0.75
1.5.2.5 | Show area covered | Andreas | 19 | 19 | Indicate location with buzzer /LED/coordinates | 2019-02-16 | 2.5
1.5.2.4 | Start / Stop robot | William | 10 | 10 | Test | 2019-02-18 | 0.375
1.5.2.5 | Instruction manual | Antonio,Al-Husein | 7 | 14 | Get connection with robot | 2019-02-09 | 4
1.5.2.6 | Test | All | 2 | 10 | Process data from robot | 2019-02-13 | 5.25
1.5.3 | GUI |  | 26 | 54 | Send data | 2019-02-19 | 4
1.5.3.2 | Mockup | All | 7 | 35 | Indicate location with buzzer /LED/coordinates | 2019-02-18 | 2.5
1.5.3.2 | Implement mockup | Fleury | 11 | 11 | Test | 2019-02-24 | 0.5
1.5.3.3 | Test | Fleury | 8 | 8 | Research | 2019-02-18 | 2.5
1.6 | Bluetooth |  | 142.5 | 317 | Config CubeMX | 2019-02-18 | 0.25
1.6.1 | Research | All | 10 | 50 | Process data from Pozyx | 2019-02-18 | 10
1.6.2 | Robot |  | 67.5 | 135 | Calculate coordinates | 2019-02-20 | 7.5
1.6.2.1 | Get connection with app | William,Andreas | 16 | 32 | Keep robot within search area | 2019-02-19 | 7.5
1.6.2.2 | Process data from app | Andreas,Alhusein | 21 | 42 | Drive to coordinate | 2019-02-23 | 12.5
1.6.2.3 | Send data | William,Alhusein | 16 | 32 | Searched area covered | 2019-02-27 | 10
1.6.2.4 | Bluetooth activity LED | Andreas | 3 | 3 | Alert location | 2019-02-26 | 7.5
1.6.2.5 | Indicate location with buzzer /LED/coordinates | Fleury,Alhusein | 10 | 20 | Test | 2019-03-04 | 0.9
1.6.2.6 | Test | Fleury,Alhusein,Andreas,William | 1.5 | 6 | Merge project | 2019-03-08 | 3.75
1.6.3 | App |  | 65 | 132 | Complete robot build | 2019-03-06 | 1.5
1.6.3.1 | Get connection with robot | Antonio, Fleury | 16 | 32 | Final tests | 2019-03-11 | 3
1.6.3.2 | Process data from robot | Antonio, Fleury | 21 | 42 | User manual | 2019-03-13 | 2.5
1.6.3.3 | Send data | Antonio, Fleury | 16 | 32 | Evaluation | 2019-03-15 | 0.25
1.6.3.3 | Indicate location with buzzer /LED/coordinates | Fleury,Alhusein | 10 | 20
1.6.3.3 | Test | Antonio,Fleury,Alhusein | 2 | 6
1.7 | Location |  | 234.6 | 379
1.7.1 | Research | All | 10 | 50
1.7.2 | Config CubeMX | Andreas | 1 | 1
1.7.3 | Process data from Pozyx | William | 40 | 40
1.7.4 | Calculate coordinates | Andreas | 30 | 30
1.7.5 | Keep robot within search area | Alhusein | 30 | 30
1.7.6 | Drive to coordinate | Antonio,Fleury | 50 | 100
1.7.7 | Searched area covered | Andreas,William | 40 | 80
1.7.8 | Alert location | Alhusein | 30 | 30
1.7.9 | Test | All | 3.6 | 18
2 | Meetings
2.1 | Meetings | All | 12 | 60
3 | Finishing work
3.1 | Merge project | Al-Husein | 15 | 15
3.2 | Complete robot build | Fleury, Antonio | 6 | 12
3.3 | Final tests | All | 12 | 60
3.4 | User manual | Al-Husein, Fleury | 10 | 20
3.5 | Evaluation | All | 1 | 5
|  |  | Total Hours: | 1287
Individual hours
| Al-Husein: | 263.1
| Fleury: | 258.1
| Antonio: | 260.6
| Andreas: | 252.1
| William: | 253.1
| Total: | 1287